## Slide 1
1
Intake
2
Site visit & assessment
3
Technical evaluation
4
KMEC committee review
5
GSA board approval
6
Legal agreement
7
Contractor mobilization
)
8
Construction / installation
Administrative steps (1-6)
Implementation steps (7-8)
Scheduled monthly meeting cadence (steps 4, 5)
Five stochastic mechanisms applied across the pipeline
1. Case-level heterogeneity
PERT (admin) and lognormal (construction) duration draws per case
2. Within-case correlation
Gaussian copula across steps within a case
3. Scheduled meeting cadence
KMEC and board batch capacity per meeting
4. Capacity-dependent throughput
Load multiplier scales step duration with active caseload
5. Finite contractor crews
FIFO slot queue shared across mitigation options